## Sheet1
!!Ohm Sri Ganeshay Namah!!
Stock Market Analysis
Task No. | Task Name | Task Description | Status | Assigned Date | Finished Date | Responsible
1 | Set Up Environment | Install Python, VS Code, and necessary dependencies. Create a virtual environment.
2 | Initialize Project | Create the project folder and initialize it with essential files like main.py and requirements.txt.
3 | Install Libraries | Install libraries like kivy, requests, textblob, etc., as listed in requirements.txt.
4 | Design Folder Structure | Organize the folder structure to separate logic (e.g., scraper.py, analysis.py, etc.).
5 | Fetch News API Key | Register and get an API key for NewsAPI or another free API for fetching news articles.
6 | Write Fetch News Function | Create a function to fetch news articles using the API and handle basic errors.
7 | Test News API Integration | Test the fetch_news function by printing results to ensure it's fetching data correctly.
8 | Sentiment Analysis Function | Create a function to analyze sentiment from the fetched news using the TextBlob library.
9 | Test Sentiment Analysis | Test the sentiment analysis function with sample text or fetched news articles.
10 | Set Up Kivy UI | Create a basic UI with input fields, buttons, and labels using the Kivy library.
11 | Link Backend with UI | Connect the UI input field to trigger the fetch and sentiment analysis functions.
12 | Display Results in UI | Update the UI to display the fetched news headlines and the sentiment recommendation.
13 | Refine Error Handling | Add proper error handling for API failures, no results, or invalid inputs.
14 | Optimize Code Structure | Modularize the code by separating logic into different files (scraper.py, analysis.py, etc.).
15 | Test Full Application | Test the full flow: user input, API call, sentiment analysis, and displaying results.
16 | Create APK File | Install Buildozer, set up buildozer.spec, and build the APK for Android.
17 | Test APK on Device | Install and test the APK on an Android device for functionality and UI performance.
18 | Create EXE File | Use PyInstaller to create a standalone EXE file for Windows.
19 | Test EXE on Windows | Run the EXE file on a Windows machine to verify functionality and UI performance.
20 | Document API Usage | Create a guide for how the News API or other APIs are used, including sample calls and responses.
21 | Write User Guide | Write a short user manual explaining how to use the application, both for Android and Windows users.
22 | Add Advanced Features | (Optional) Add features like charts for historical data or advanced sentiment analysis using NLP.
23 | Final Testing | Perform comprehensive testing to ensure the app works across devices and scenarios.
24 | Deploy APK | Share the APK via Google Drive or upload to the Google Play Store.
25 | Share EXE | Share the EXE file with users via direct download or packaging.