## Sheet1
!!Ohm Sri Ganeshay Namah!!
Stock Market Analysis
Task No. | Task Name | Task Description | Status | Assigned Date | Finished Date | Responsible
1 | Set Up Environment | Install Python, VS Code, and necessary dependencies. Create a virtual environment.
2 | Initialize Project | Create the project folder and initialize it with essential files like main.py and requirements.txt.
3 | Install Libraries | Install libraries like kivy, requests, textblob, etc., as listed in requirements.txt.
4 | Design Folder Structure | Organize the folder structure to separate logic (e.g., scraper.py, analysis.py, etc.).
5 | Fetch News API Key | Register and get an API key for NewsAPI or another free API for fetching news articles.
6 | Write Fetch News Function | Create a function to fetch news articles using the API and handle basic errors.
7 | Test News API Integration | Test the fetch_news function by printing results to ensure it's fetching data correctly.
8 | Sentiment Analysis Function | Create a function to analyze sentiment from the fetched news using the TextBlob library.
9 | Test Sentiment Analysis | Test the sentiment analysis function with sample text or fetched news articles.
10 | Set Up Kivy UI | Create a basic UI with input fields, buttons, and labels using the Kivy library.
11 | Link Backend with UI | Connect the UI input field to trigger the fetch and sentiment analysis functions.
12 | Display Results in UI | Update the UI to display the fetched news headlines and the sentiment recommendation.
13 | Refine Error Handling | Add proper error handling for API failures, no results, or invalid inputs.
14 | Optimize Code Structure | Modularize the code by separating logic into different files (scraper.py, analysis.py, etc.).
15 | Test Full Application | Test the full flow: user input, API call, sentiment analysis, and displaying results.
16 | Create APK File | Install Buildozer, set up buildozer.spec, and build the APK for Android.
17 | Test APK on Device | Install and test the APK on an Android device for functionality and UI performance.
18 | Create EXE File | Use PyInstaller to create a standalone EXE file for Windows.
19 | Test EXE on Windows | Run the EXE file on a Windows machine to verify functionality and UI performance.
20 | Document API Usage | Create a guide for how the News API or other APIs are used, including sample calls and responses.
21 | Write User Guide | Write a short user manual explaining how to use the application, both for Android and Windows users.
22 | Add Advanced Features | (Optional) Add features like charts for historical data or advanced sentiment analysis using NLP.
23 | Final Testing | Perform comprehensive testing to ensure the app works across devices and scenarios.
24 | Deploy APK | Share the APK via Google Drive or upload to the Google Play Store.
25 | Share EXE | Share the EXE file with users via direct download or packaging.
1. Planning and Setup
| Task ID | Task Name | Task Description
| P1 | Define Project Requirements | Identify core features, tools, and technologies for the project.
| P2 | Create Project Repository | Set up a GitHub repository to track project progress and code.
| P3 | Set Up Environment | Configure the Python environment and dependencies.
| P4 | Prepare Docker Setup | Write the initial Dockerfile and test the environment setup.
2. Backend Development
| Task ID | Task Name | Task Description
| B1 | Research Free Stock APIs | Identify and test free APIs (e.g., NewsAPI, Finnhub) for news data.
| B2 | Fetch Stock Data | Implement a module to fetch stock-related news using the API.
| B3 | Parse API Data | Extract relevant information from the API responses.
| B4 | Develop Sentiment Analysis | Create a module to analyze sentiment using TextBlob or similar.
| B5 | Combine News & Analysis | Integrate news fetching and sentiment analysis into one function.
3. Frontend Development
| Task ID | Task Name | Task Description
| F1 | Design App UI (Kivy) | Build a basic user interface for entering stock names.
| F2 | Add Input Field | Create an input field for the user to enter a company name.
| F3 | Display Analysis Results | Show sentiment scores and "Buy" or "Sell" recommendations.
| F4 | Error Handling in UI | Add error messages for invalid inputs or API failures.
4. Testing
| Task ID | Task Name | Task Description
| T1 | Unit Testing API Module | Write test cases for the API-fetching logic.
| T2 | Unit Testing Sentiment Module | Write test cases for the sentiment analysis module.
| T3 | Frontend Integration Testing | Ensure frontend and backend modules work together.
| T4 | Cross-Platform Testing | Test the app on multiple platforms (Linux, Windows, Android).
5. Deployment
| Task ID | Task Name | Task Description
| D1 | Build APK (Buildozer) | Generate the Android APK using Buildozer.
| D2 | Build EXE (PyInstaller) | Generate the Windows EXE using PyInstaller.
| D3 | Create Docker Image | Build and test the Docker container for the app.
| D4 | Publish Docker Image | Push the Docker image to a public registry like Docker Hub.
6. Documentation
| Task ID | Task Name | Task Description
| DC1 | Write README File | Create a comprehensive README.md for the project.
| DC2 | API Key Configuration Guide | Document how to obtain and configure API keys.
| DC3 | Docker Usage Guide | Provide instructions for building and running the Docker container.
| DC4 | Deployment Guide | Document APK and EXE generation processes.
7. Enhancement and Future Tasks
| Task ID | Task Name | Task Description
| E1 | Advanced Sentiment Analysis | Use machine learning libraries like TensorFlow or PyTorch.
| E2 | Historical Stock Analysis | Integrate historical stock data for trend analysis.
| E3 | Graphical Results | Add graphs to display sentiment trends.
| E4 | Notification System | Implement notifications for critical news updates.
Workflow in Asana
1. Create Sections: Each stage (Planning, Backend Development, etc.) can be a section in Asana.
2. Add Tasks: Enter the tasks into Asana with their IDs and descriptions.
3. Assign Tasks: Assign tasks to team members.
4. Track Progress: Use Asana’s features to set deadlines, add comments, and mark tasks as complete.
Would you like help in writing Asana-specific task descriptions or templates for these activities?